## TODO
TODO LIST
Programming | Art | Combined | KEY
load/use new character mesh | determine menu designs | write out various effects that character control has on gameplay | DONE
determine what causes differences in launch trajectories (something with collision bodies?) | button & menu interaction |  | NOT DONE
weight ragdoll's feet to get it to tend toward falling feet first |  | determine how to do upgrades & currency-related features | NOT NEEDED
determine how to have glass break |  |  | table is sorted by color, no color
Develop wall jump |  |  | todos are placed at the top
Create rough versions of the rest of world 1 levels |  | figure out if vertex anim/morphs are possible (script?)
Allow changing the current level to any level for testing purposes
Add dynamic creation of chain rope, being able to add various amount of links through an editor property
handle hitting spikes
fine-tune following camera, resetting
fine-tune trampoline bounciness
code for moving see-saw to new location
setup rope prefab (character able to jump on/off) |  | Moving up/down rope - do they automatically stop moving when they get to the bottom, or does that cause them to let go??
Raise ceiling a bit |  | Need to know exactly how camera will operate
determine scale of everything so, figure out a standard for block sizes |  | determine exactly how moving see-saw to new location will work
determine how to blend from ragdoll to an animation | SCALE IS 6.5 | Determine how we want resetting to work for sure…do we move see saw, subtract health, etc. Flow chart would be good: player comes to rest…what happens after this??? at what point does the character get reset, e.g. when he doesn't "die" but doesn't reach a checkpoint or goal....when he stops moving completely or when he's below a certain velocity? When he does get reset, is it a loss of life? health? or something else entirely?

## History & Critiques
History & Critiques
Version | Changes | Critiques
v 0.1 | Rough version of see-saw, player camera, trampoline effect, & character control. Weight & wedge movement. Finish condition & scene change. Restart & reset.
v 0.2 | New version of everything mostly. Need comments/suggestions on camera & see-saw functionality. Prefabs for see-saw, game object, sun, player, player camera, trampoline, wall spikes, ground spikes. Different (cleaner) scripting for everything. | To have two main cameras that quickly zoom between each other; adding perspective to the 3D side scroll style. One camera display the entire level, the other centering on the character; adding some drag to the camera would feel more natural.
v 0.3 | Better camera following Sped up time a bit. Fixed some reset problems.
v 0.4 | Camera now interpolates between 2 positions for zoom in/out
v 0.5 | Added ceiling and back wall added rough main menu, transition with play button start level with camera zoomed out on entire level, wait a bit, then zoom in on see-saw | Camera movement is very smooth. Practice level has floor, backing, and a ceiling, its nice to know what your limits are in the beginning of a game, and to exceed them over time. The character motion was at good speed; I think the landing should be a harder drop, like the character "spacks" the ground, maybe a short skid. ( I actually, flung myelf into the ceiling and it was awesome, it just bounced off straight to the ground.) I also enjoy the movement on the pivot point and the weight, they seem to be smoother as well. and the see-saw to triangle ratio is more aesthetically pleasing.
v 0.6 | Added rough trampoline prefab with scripting Basic bounciness for trampoline, needs work
v 0.7 | Jump pad now uses player's velocity to determine force player is propelled away with
v 0.8 | Jump pads more realistic, feel better brought zoomed in cam out a bit, Cam now follows the player's y movement
v 0.9.1 | Added a second level to test transitioning Added defeat scene Added code to die when spikes are hit Added delay for reset after dying Added lives & health (in code only) | The flow is getting to a really good point! And the new camera adjustment adds a lot more to it. I think the player should be able to bring the weight a little bit farther down closer to the see-saw; in order to create a short hop over objects. I like the limits side-to-side. The bouce amount from the jump pads can have more spring to them, propelling the character farther. The level change adds an extra encentive to completing the level, and allows more personal gain, nice touch.
v 0.10 | Rearranged levels 1 & 2 to be like concepts Tweaked bounce pads to be more responsive Added text for death Character stops movement when hitting spikes Bug fixes for lives counter, resetting correctly… Added prefabs for spiked walls, left facing, right facing, both sides increased range for weight movement
v 0.11 | See-saw now moves to the last place your character stopped if you have enough health Keeping track of health and displaying Reset health when lives get decremented Increased zoomed out camera distance slightly
v 0.12 | Added chain rope prefab, player can grab onto it and let go by pressing/releasing 'J'
v 0.13 | Chain rope now can be grabbed correctly no matter what position/orientation it has Area to grab onto rope decreased, making where the player is in relation to the rope more realistic looking.
v0.14 | Added rough up/down movement for rope Added rope reset Raised the roof!
v0.15 | Rope climbing up/down working, needs tweaks
v0.16 | Previous level one is now "practice" level Levels 1-4 are done similar to concept images Addition of checkpoint prefab Addition of water prefab Brought zoomed-in cam back a bit Added boost force when "J" is pressed Many minor changes to code structure & cleanup Added current world/level to HUD