## TODO_Programming
Task List - Programming
# | Category | Description | Done | Priority (1-3) | Platform (I, M, P) | Who
1 | Art Assets | test out new character model with rigging, scale | N | 1 | I, M, P | None
2 | Menus | use double-tap to bring up an in-game menu (with quit, main menu, and options as options) that functions | N | 1 | I | None
3 | Gameplay | Develop pulley system scipting | N | 2 | I, M, P | None
4 | Levels | Setup generic prefab, base structure for all levels (maybe divide into worlds with their different themes) | N | 2 | I, M, P | None
5 | Object Interaction | Develop fan functionality | N | 2 | I, M, P | None
6 | Object Interaction | Develop cauldron functionality | N | 2 | I, M, P | None
7 | Object Interaction | Develop collection functionality (make general) | N | 2 | I, M, P | None
8 | Objects | Create fan prefab | N | 2 | I, M, P | None
9 | Objects | Create cauldron prefab | N | 2 | I, M, P | None
10 | Objects | Change spike prefabs to contain fewer spikes depth-wise | N | 2 | I, M, P | None
11 | Objects | Create Energy Collectible prefab | N | 2 | I, M, P | None
12 | Visuals | Perfect trajectory | N | 2 | I, M, P | None
13 | Art Assets/Objects | determine how to have glass break, pre-broken mesh, need access to separate meshes' data? | N | 3 | I, M, P | None
14 | Cameras | Dynamically calculate range for camera pan left/right | N | 3 | I, M, P | None
15 | Menus | Create generic menu slider (e.g. volume) for options menu | N | 3 | I, M, P | None
16 | Menus | Create generic menu toggle (e.g. switch sound on/off, use arrows) | N | 3 | I, M, P | None
17 | Menus | Develop automatically generated Options Menu list of options based on platform | N | 3 | I, M, P | None
18 | Menus | Add currently selected functionality to menu options (i.e. you can't select it again if it's already selected) | N | 3 | I, M, P | None
19 | Objects | Add dynamic creation of chain rope, being able to add various amount of links through an editor property | N | 3 | I, M, P | None
20 | Abilities | Develop wall jump | Y | 1 | I, M, P | Ray
21 | Art Assets | determine scale of everything, figure out a standard for block sizes | Y | 1 | I, M, P | Ray
22 | Cameras | fine-tune following camera, resetting | Y | 1 | I, M, P | Ray
23 | Levels | Create rough versions of the rest of world 1 levels | Y | 1 | I, M, P | Ray
24 | Menus | Allow level selection | Y | 1 | I, M, P | Ray
25 | Movement | smooth out movement for direction change (accelerometer) | Y | 1 | I | Ray
26 | Object Interaction | handle hitting spikes | Y | 1 | I, M, P | Ray
27 | Objects | setup rope prefab (character able to jump on/off) | Y | 1 | I, M, P | Ray
28 | Abilities | make boost only available when in range of pad | Y | 2 | I, M, P | Ray
29 | Cameras | have camera look ahead of the player a bit (especially when falling) | Y | 2 | I, M, P | Ray
30 | Gameplay | code for moving see-saw to new location | Y | 2 | I, M, P | Ray
31 | Levels | Raise ceiling a bit | Y | 2 | I, M, P | Ray
32 | Movement | make side-side movement able to be controlled more | Y | 2 | I, M, P | Ray
33 | Movement | speed up movement (increase delta time) | Y | 2 | I, M, P | Ray
34 | Object Interaction | add going through bottom of one-way jump pad | Y | 2 | I, M, P | Ray
35 | Object Interaction | add bouncing on both sides of jump pad | Y | 2 | I, M, P | Ray
36 | Object Interaction | add max/min velocities for jump pad | Y | 2 | I, M, P | Ray
37 | Object Interaction | fine-tune trampoline bounciness | Y | 2 | I, M, P | Ray
38 | Cameras | store distance that player zooms in/out and use that for zoomed pos in after level intro | Y | 3 | I, M, P | Ray
39 | Visuals | remove trajectory shortly after launch | Y | 3 | I, M, P | Ray
40 | [5 empty] | None
41 | [5 empty] | None
42 | [5 empty] | None
43 | [5 empty] | None
44 | [5 empty] | None
45 | [5 empty] | None
46 | [5 empty] | None
47 | [5 empty] | None
48 | [5 empty] | None
49 | [5 empty] | None
50 | [5 empty] | None
51 | [5 empty] | None
52 | [5 empty] | None
53 | [5 empty] | None
54 | [5 empty] | None
55 | [5 empty] | None
56 | [5 empty] | None
57 | [5 empty] | None
58 | [5 empty] | None
59 | [5 empty] | None
60 | [5 empty] | None
61 | [5 empty] | None
62 | [5 empty] | None
63 | [5 empty] | None
64 | [5 empty] | None
65 | [5 empty] | None
66 | [5 empty] | None
67 | [5 empty] | None
68 | [5 empty] | None
69 | [5 empty] | None
70 | [5 empty] | None
71 | [5 empty] | None
72 | [5 empty] | None
73 | [5 empty] | None
74 | [5 empty] | None
75 | [5 empty] | None
76 | [5 empty] | None
77 | [5 empty] | None
78 | [5 empty] | None
79 | [5 empty] | None
80 | [5 empty] | None
81 | [5 empty] | None
82 | [5 empty] | None
83 | [5 empty] | None
84 | [5 empty] | None
85 | [5 empty] | None
86 | [5 empty] | None
87 | [5 empty] | None
88 | [5 empty] | None
89 | [5 empty] | None
90 | [5 empty] | None
91 | [5 empty] | None
92 | [5 empty] | None
93 | [5 empty] | None
94 | [5 empty] | None
95 | [5 empty] | None
96 | [5 empty] | None
97 | [5 empty] | None
98 | [5 empty] | None
99 | [5 empty] | None
100 | [5 empty] | None
101 | [5 empty] | None
102 | [5 empty] | None
103 | [5 empty] | None
104 | [5 empty] | None
105 | [5 empty] | None
106 | [5 empty] | None
107 | [5 empty] | None
108 | [5 empty] | None
109 | [5 empty] | None
110 | [5 empty] | None
111 | [5 empty] | None
112 | [5 empty] | None
113 | [5 empty] | None
114 | [5 empty] | None
115 | [5 empty] | None
116 | [5 empty] | None
117 | [5 empty] | None
118 | [5 empty] | None
119 | [5 empty] | None
120 | [5 empty] | None
121 | [5 empty] | None
122 | [5 empty] | None
123 | [5 empty] | None
124 | [5 empty] | None
125 | [5 empty] | None
126 | [5 empty] | None
127 | [5 empty] | None
128 | [5 empty] | None
129 | [5 empty] | None
130 | [5 empty] | None
131 | [5 empty] | None
132 | [5 empty] | None
133 | [5 empty] | None
134 | [5 empty] | None
135 | [5 empty] | None
136 | [5 empty] | None
137 | [5 empty] | None
138 | [5 empty] | None
139 | [5 empty] | None
140 | [5 empty] | None
141 | [5 empty] | None
142 | [5 empty] | None
143 | [5 empty] | None
144 | [5 empty] | None
145 | [5 empty] | None
146 | [5 empty] | None
147 | [5 empty] | None
148 | [5 empty] | None
149 | [5 empty] | None
150 | [5 empty] | None
151 | [5 empty] | None
152 | [5 empty] | None
153 | [5 empty] | None
154 | [5 empty] | None
155 | [5 empty] | None
156 | [5 empty] | None
157 | [5 empty] | None
158 | [5 empty] | None
159 | [5 empty] | None
160 | [5 empty] | None
161 | [5 empty] | None
162 | [5 empty] | None
163 | [5 empty] | None
164 | [5 empty] | None
165 | [5 empty] | None
166 | [5 empty] | None
167 | [5 empty] | None
168 | [5 empty] | None
169 | [5 empty] | None
170 | [5 empty] | None
171 | [5 empty] | None
172 | [5 empty] | None
173 | [5 empty] | None
174 | [5 empty] | None
175 | [5 empty] | None
176 | [5 empty] | None
177 | [5 empty] | None
178 | [5 empty] | None
179 | [5 empty] | None
180 | [5 empty] | None
181 | [5 empty] | None
182 | [5 empty] | None
183 | [5 empty] | None
184 | [5 empty] | None
185 | [5 empty] | None
186 | [5 empty] | None
187 | [5 empty] | None
188 | [5 empty] | None
189 | [5 empty] | None
190 | [5 empty] | None
191 | [5 empty] | None
192 | [5 empty] | None
193 | [5 empty] | None
194 | [5 empty] | None
195 | [5 empty] | None
196 | [5 empty] | None
197 | [5 empty] | None
198 | [5 empty] | None
199 | [5 empty] | None
200 | [5 empty] | None
201 | [5 empty] | None
202 | [5 empty] | None
203 | [5 empty] | None
204 | [5 empty] | None
205 | [5 empty] | None
206 | [5 empty] | None
207 | [5 empty] | None
208 | [5 empty] | None
209 | [5 empty] | None
210 | [5 empty] | None
211 | [5 empty] | None
212 | [5 empty] | None
213 | [5 empty] | None
214 | [5 empty] | None
215 | [5 empty] | None
216 | [5 empty] | None
217 | [5 empty] | None
218 | [5 empty] | None
219 | [5 empty] | None
220 | [5 empty] | None
221 | [5 empty] | None
222 | [5 empty] | None
223 | [5 empty] | None
224 | [5 empty] | None
225 | [5 empty] | None
226 | [5 empty] | None
227 | [5 empty] | None
228 | [5 empty] | None
229 | [5 empty] | None
230 | [5 empty] | None
231 | [5 empty] | None
232 | [5 empty] | None
233 | [5 empty] | None
234 | [5 empty] | None
235 | [5 empty] | None
236 | [5 empty] | None
237 | [5 empty] | None
238 | [5 empty] | None
239 | [5 empty] | None
240 | [5 empty] | None
241 | [5 empty] | None
242 | [5 empty] | None
243 | [5 empty] | None
244 | [5 empty] | None
245 | [5 empty] | None
246 | [5 empty] | None
247 | [5 empty] | None
248 | [5 empty] | None
249 | [5 empty] | None
250 | [5 empty] | None
251 | [5 empty] | None
252 | [5 empty] | None
253 | [5 empty] | None
254 | [5 empty] | None
255 | [5 empty] | None
256 | [5 empty] | None
257 | [5 empty] | None
258 | [5 empty] | None
259 | [5 empty] | None
260 | [5 empty] | None
261 | [5 empty] | None
262 | [5 empty] | None
263 | [5 empty] | None
264 | [5 empty] | None
265 | [5 empty] | None
266 | [5 empty] | None
267 | [5 empty] | None
268 | [5 empty] | None
269 | [5 empty] | None
270 | [5 empty] | None
271 | [5 empty] | None
272 | [5 empty] | None
273 | [5 empty] | None
274 | [5 empty] | None
275 | [5 empty] | None
276 | [5 empty] | None
277 | [5 empty] | None
278 | [5 empty] | None
279 | [5 empty] | None
280 | [5 empty] | None
281 | [5 empty] | None
282 | [5 empty] | None
283 | [5 empty] | None
284 | [5 empty] | None
285 | [5 empty] | None
286 | [5 empty] | None
287 | [5 empty] | None
288 | [5 empty] | None
289 | [5 empty] | None
290 | [5 empty] | None
291 | [5 empty] | None
292 | [5 empty] | None
293 | [5 empty] | None
294 | [5 empty] | None
295 | [5 empty] | None
296 | [5 empty] | None
297 | [5 empty] | None
298 | [5 empty] | None
299 | [5 empty] | None
300 | [5 empty] | None
301 | [5 empty] | None
302 | [5 empty] | None
303 | [5 empty] | None
304 | [5 empty] | None
305 | [5 empty] | None
306 | [5 empty] | None
307 | [5 empty] | None
308 | [5 empty] | None
309 | [5 empty] | None
310 | [5 empty] | None
311 | [5 empty] | None
312 | [5 empty] | None
313 | [5 empty] | None
314 | [5 empty] | None
315 | [5 empty] | None
316 | [5 empty] | None
317 | [5 empty] | None
318 | [5 empty] | None
319 | [5 empty] | None
320 | [5 empty] | None
321 | [5 empty] | None
322 | [5 empty] | None
323 | [5 empty] | None
324 | [5 empty] | None
325 | [5 empty] | None
326 | [5 empty] | None
327 | [5 empty] | None
328 | [5 empty] | None
329 | [5 empty] | None
330 | [5 empty] | None
331 | [5 empty] | None
332 | [5 empty] | None
333 | [5 empty] | None
334 | [5 empty] | None
335 | [5 empty] | None
336 | [5 empty] | None
337 | [5 empty] | None
338 | [5 empty] | None
339 | [5 empty] | None
340 | [5 empty] | None
341 | [5 empty] | None
342 | [5 empty] | None
343 | [5 empty] | None
344 | [5 empty] | None
345 | [5 empty] | None
346 | [5 empty] | None
347 | [5 empty] | None
348 | [5 empty] | None
349 | [5 empty] | None
350 | [5 empty] | None
351 | [5 empty] | None
352 | [5 empty] | None
353 | [5 empty] | None
354 | [5 empty] | None
355 | [5 empty] | None
356 | [5 empty] | None
357 | [5 empty] | None
358 | [5 empty] | None
359 | [5 empty] | None
360 | [5 empty] | None
361 | [5 empty] | None
362 | [5 empty] | None
363 | [5 empty] | None
364 | [5 empty] | None
365 | [5 empty] | None
366 | [5 empty] | None
367 | [5 empty] | None
368 | [5 empty] | None
369 | [5 empty] | None
370 | [5 empty] | None
371 | [5 empty] | None
372 | [5 empty] | None
373 | [5 empty] | None
374 | [5 empty] | None
375 | [5 empty] | None
376 | [5 empty] | None
377 | [5 empty] | None
378 | [5 empty] | None
379 | [5 empty] | None
380 | [5 empty] | None
381 | [5 empty] | None
382 | [5 empty] | None
383 | [5 empty] | None
384 | [5 empty] | None
385 | [5 empty] | None
386 | [5 empty] | None
387 | [5 empty] | None
388 | [5 empty] | None
389 | [5 empty] | None
390 | [5 empty] | None
391 | [5 empty] | None
392 | [5 empty] | None
393 | [5 empty] | None
394 | [5 empty] | None
395 | [5 empty] | None
396 | [5 empty] | None
397 | [5 empty] | None
398 | [5 empty] | None
399 | [5 empty] | None
400 | [5 empty] | None
401 | [5 empty] | None
402 | [5 empty] | None
403 | [5 empty] | None
404 | [5 empty] | None
405 | [5 empty] | None
406 | [5 empty] | None
407 | [5 empty] | None
408 | [5 empty] | None
409 | [5 empty] | None
410 | [5 empty] | None
411 | [5 empty] | None
412 | [5 empty] | None
413 | [5 empty] | None
414 | [5 empty] | None
415 | [5 empty] | None
416 | [5 empty] | None
417 | [5 empty] | None
418 | [5 empty] | None
419 | [5 empty] | None
420 | [5 empty] | None
421 | [5 empty] | None
422 | [5 empty] | None
423 | [5 empty] | None
424 | [5 empty] | None
425 | [5 empty] | None
426 | [5 empty] | None
427 | [5 empty] | None
428 | [5 empty] | None
429 | [5 empty] | None
430 | [5 empty] | None
431 | [5 empty] | None
432 | [5 empty] | None
433 | [5 empty] | None
434 | [5 empty] | None
435 | [5 empty] | None
436 | [5 empty] | None
437 | [5 empty] | None
438 | [5 empty] | None
439 | [5 empty] | None
440 | [5 empty] | None
441 | [5 empty] | None
442 | [5 empty] | None
443 | [5 empty] | None
444 | [5 empty] | None
445 | [5 empty] | None
446 | [5 empty] | None
447 | [5 empty] | None
448 | [5 empty] | None
449 | [5 empty] | None
450 | [5 empty] | None
451 | [5 empty] | None
452 | [5 empty] | None
453 | [5 empty] | None
454 | [5 empty] | None
455 | [5 empty] | None
456 | [5 empty] | None
457 | [5 empty] | None
458 | [5 empty] | None
459 | [5 empty] | None
460 | [5 empty] | None
461 | [5 empty] | None
462 | [5 empty] | None
463 | [5 empty] | None
464 | [5 empty] | None
465 | [5 empty] | None
466 | [5 empty] | None
467 | [5 empty] | None
468 | [5 empty] | None
469 | [5 empty] | None
470 | [5 empty] | None
471 | [5 empty] | None
472 | [5 empty] | None
473 | [5 empty] | None
474 | [5 empty] | None
475 | [5 empty] | None
476 | [5 empty] | None
477 | [5 empty] | None
478 | [5 empty] | None
479 | [5 empty] | None
480 | [5 empty] | None
481 | [5 empty] | None
482 | [5 empty] | None
483 | [5 empty] | None
484 | [5 empty] | None
485 | [5 empty] | None
486 | [5 empty] | None
487 | [5 empty] | None
488 | [5 empty] | None
489 | [5 empty] | None
490 | [5 empty] | None
491 | [5 empty] | None
492 | [5 empty] | None
493 | [5 empty] | None
494 | [5 empty] | None
495 | [5 empty] | None
496 | [5 empty] | None
497 | [5 empty] | None
498 | [5 empty] | None
499 | [5 empty] | None
500 | [5 empty] | None
501 | [5 empty] | None
502 | [5 empty] | None
503 | [5 empty] | None
504 | [5 empty] | None
505 | [5 empty] | None
506 | [5 empty] | None
507 | [5 empty] | None
508 | [5 empty] | None
509 | [5 empty] | None
510 | [5 empty] | None
511 | [5 empty] | None
512 | [5 empty] | None
513 | [5 empty] | None
514 | [5 empty] | None
515 | [5 empty] | None
516 | [5 empty] | None
517 | [5 empty] | None
518 | [5 empty] | None
519 | [5 empty] | None
520 | [5 empty] | None
521 | [5 empty] | None
522 | [5 empty] | None
523 | [5 empty] | None
524 | [5 empty] | None
525 | [5 empty] | None
526 | [5 empty] | None
527 | [5 empty] | None
528 | [5 empty] | None
529 | [5 empty] | None
530 | [5 empty] | None
531 | [5 empty] | None
532 | [5 empty] | None
533 | [5 empty] | None
534 | [5 empty] | None
535 | [5 empty] | None
536 | [5 empty] | None
537 | [5 empty] | None
538 | [5 empty] | None
539 | [5 empty] | None
540 | [5 empty] | None
541 | [5 empty] | None
542 | [5 empty] | None
543 | [5 empty] | None
544 | [5 empty] | None
545 | [5 empty] | None
546 | [5 empty] | None
547 | [5 empty] | None
548 | [5 empty] | None
549 | [5 empty] | None
550 | [5 empty] | None
551 | [5 empty] | None
552 | [5 empty] | None
553 | [5 empty] | None
554 | [5 empty] | None
555 | [5 empty] | None
556 | [5 empty] | None
557 | [5 empty] | None
558 | [5 empty] | None
559 | [5 empty] | None
560 | [5 empty] | None
561 | [5 empty] | None
562 | [5 empty] | None
563 | [5 empty] | None
564 | [5 empty] | None
565 | [5 empty] | None
566 | [5 empty] | None
567 | [5 empty] | None
568 | [5 empty] | None
569 | [5 empty] | None
570 | [5 empty] | None
571 | [5 empty] | None
572 | [5 empty] | None
573 | [5 empty] | None
574 | [5 empty] | None
575 | [5 empty] | None
576 | [5 empty] | None
577 | [5 empty] | None
578 | [5 empty] | None
579 | [5 empty] | None
580 | [5 empty] | None
581 | [5 empty] | None
582 | [5 empty] | None
583 | [5 empty] | None
584 | [5 empty] | None
585 | [5 empty] | None
586 | [5 empty] | None
587 | [5 empty] | None
588 | [5 empty] | None
589 | [5 empty] | None
590 | [5 empty] | None
591 | [5 empty] | None

## TODO_Art
Task List - Art
# | Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19 | Column20 | Column21 | Column22
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591

## Bugs
BUGS
# | General | Description | Script | Priority (1-3) | Fixed | What fixed it? | Platforms (I, M, P)
1 | 1-way jump pad | If you jump through from underneath with too little force and don't go far enough above the jump pad, character gets stuck and no longer bounces and cannot use jump | Trampoline.cs | 1 | N |  | I
2 | 2-way jump pad | Sometimes if you land on the top without jumping the character will get stuck in a small up/down movement pattern | Trampoline.cs | 1 | N |  | I
3 | 2-way jump pad | Bottom bounce acts like hitting a wall, instead of an elastic object | Trampoline.cs | 2 | N |  | I
4 | Menu animation | Screws don't animate on click | MenuOption.cs | 3 | Y - Ray | Calling Play on Bolt.animation in the iPhone's input area | I
5 | Set Weight height | Area where weight can be "grabbed" by touch is too small | Weight.cs | 2 | N |  | I
6 | Set Wedge position | Area where wedge can be "grabbed" by touch is too small | Wedge.cs | 2 | N |  | I
7 |  |  |  |  | N
8 |  |  |  |  | N
9 |  |  |  |  | N
10 |  |  |  |  | N
11 |  |  |  |  | N
12 |  |  |  |  | N
13 |  |  |  |  | N
14 |  |  |  |  | N
15 |  |  |  |  | N
16 |  |  |  |  | N
17 |  |  |  |  | N
18 |  |  |  |  | N
19 |  |  |  |  | N
20 |  |  |  |  | N
21 |  |  |  |  | N
22 |  |  |  |  | N
23 |  |  |  |  | N
24 |  |  |  |  | N
25 |  |  |  |  | N
26 |  |  |  |  | N
27 |  |  |  |  | N
28 |  |  |  |  | N
29 |  |  |  |  | N
30 |  |  |  |  | N
31 |  |  |  |  | N
32 |  |  |  |  | N
33 |  |  |  |  | N
34 |  |  |  |  | N
35 |  |  |  |  | N
36 |  |  |  |  | N
37 |  |  |  |  | N
38 |  |  |  |  | N
39 |  |  |  |  | N
40 |  |  |  |  | N
41 |  |  |  |  | N
42 |  |  |  |  | N
43 |  |  |  |  | N
44 |  |  |  |  | N
45 |  |  |  |  | N
46 |  |  |  |  | N
47 |  |  |  |  | N
48 |  |  |  |  | N
49 |  |  |  |  | N
50 |  |  |  |  | N
51 |  |  |  |  | N
52 |  |  |  |  | N
53 |  |  |  |  | N
54 |  |  |  |  | N
55 |  |  |  |  | N
56 |  |  |  |  | N
57 |  |  |  |  | N
58 |  |  |  |  | N
59 |  |  |  |  | N
60 |  |  |  |  | N
61 |  |  |  |  | N
62 |  |  |  |  | N
63 |  |  |  |  | N
64 |  |  |  |  | N
65 |  |  |  |  | N
66 |  |  |  |  | N
67 |  |  |  |  | N
68 |  |  |  |  | N
69 |  |  |  |  | N
70 |  |  |  |  | N
71 |  |  |  |  | N
72 |  |  |  |  | N
73 |  |  |  |  | N
74 |  |  |  |  | N
75 |  |  |  |  | N
76 |  |  |  |  | N
77 |  |  |  |  | N
78 |  |  |  |  | N
79 |  |  |  |  | N
80 |  |  |  |  | N
81 |  |  |  |  | N
82 |  |  |  |  | N
83 |  |  |  |  | N
84 |  |  |  |  | N
85 |  |  |  |  | N
86 |  |  |  |  | N
87 |  |  |  |  | N
88 |  |  |  |  | N
89 |  |  |  |  | N
90 |  |  |  |  | N
91 |  |  |  |  | N
92 |  |  |  |  | N
93 |  |  |  |  | N
94 |  |  |  |  | N
95 |  |  |  |  | N
96 |  |  |  |  | N
97 |  |  |  |  | N

## History & Critiques
History & Critiques
Version | Changes | Critiques
v 0.1 | Rough version of see-saw, player camera, trampoline effect, & character control. Weight & wedge movement. Finish condition & scene change. Restart & reset.
v 0.2 | New version of everything mostly. Need comments/suggestions on camera & see-saw functionality. Prefabs for see-saw, game object, sun, player, player camera, trampoline, wall spikes, ground spikes. Different (cleaner) scripting for everything. | To have two main cameras that quickly zoom between each other; adding perspective to the 3D side scroll style. One camera display the entire level, the other centering on the character; adding some drag to the camera would feel more natural.
v 0.3 | Better camera following Sped up time a bit. Fixed some reset problems.
v 0.4 | Camera now interpolates between 2 positions for zoom in/out
v 0.5 | Added ceiling and back wall added rough main menu, transition with play button start level with camera zoomed out on entire level, wait a bit, then zoom in on see-saw | Camera movement is very smooth. Practice level has floor, backing, and a ceiling, its nice to know what your limits are in the beginning of a game, and to exceed them over time. The character motion was at good speed; I think the landing should be a harder drop, like the character "spacks" the ground, maybe a short skid. ( I actually, flung myelf into the ceiling and it was awesome, it just bounced off straight to the ground.) I also enjoy the movement on the pivot point and the weight, they seem to be smoother as well. and the see-saw to triangle ratio is more aesthetically pleasing.
v 0.6 | Added rough trampoline prefab with scripting Basic bounciness for trampoline, needs work
v 0.7 | Jump pad now uses player's velocity to determine force player is propelled away with
v 0.8 | Jump pads more realistic, feel better brought zoomed in cam out a bit, Cam now follows the player's y movement
v 0.9.1 | Added a second level to test transitioning Added defeat scene Added code to die when spikes are hit Added delay for reset after dying Added lives & health (in code only) | The flow is getting to a really good point! And the new camera adjustment adds a lot more to it. I think the player should be able to bring the weight a little bit farther down closer to the see-saw; in order to create a short hop over objects. I like the limits side-to-side. The bouce amount from the jump pads can have more spring to them, propelling the character farther. The level change adds an extra encentive to completing the level, and allows more personal gain, nice touch.
v 0.10 | Rearranged levels 1 & 2 to be like concepts Tweaked bounce pads to be more responsive Added text for death Character stops movement when hitting spikes Bug fixes for lives counter, resetting correctly… Added prefabs for spiked walls, left facing, right facing, both sides increased range for weight movement
v 0.11 | See-saw now moves to the last place your character stopped if you have enough health Keeping track of health and displaying Reset health when lives get decremented Increased zoomed out camera distance slightly
v 0.12 | Added chain rope prefab, player can grab onto it and let go by pressing/releasing 'J'
v 0.13 | Chain rope now can be grabbed correctly no matter what position/orientation it has Area to grab onto rope decreased, making where the player is in relation to the rope more realistic looking.
v0.14 | Added rough up/down movement for rope Added rope reset Raised the roof!
v0.15 | Rope climbing up/down working, needs tweaks
v0.16 | Previous level one is now "practice" level Levels 1-4 are done similar to concept images Addition of checkpoint prefab Addition of water prefab Brought zoomed-in cam back a bit Added boost force when "J" is pressed Many minor changes to code structure & cleanup Added current world/level to HUD
v0.17 | Levels 5-8 rough placement is done according to concepts (minus some of the different jump pads) Created script for moving objects Sped up time a bit, gameplay is a bit more fast-paced now and less "floaty" Gravity has also been increased slightly
v0.18 | Boost now only works if within range of a jump pad Rough Wall jump working modified level 7 a bit to force player to use wall jump in the beginning Level 8 wall jumping
v0.19 | Changed wall jump to stop immediately when action button 1 is pressed Increased vertical velocity of wall jump, decreased horiztonal Cap for max/min jump pad velocities, still a small bug that sometimes stalls the character on the pad Rearranged levels slightly to accomodate for lower jumping height
v0.20 | Hopefully fixed stall on jump pads Added level 9, rough version
v0.21 | Added 10th level, rough version
v0.22 | Added 1st version of trajectory prediction (close, but not finished)
v0.23 | Level selection (without level numbers) working
v0.24 | Main Menu with working buttons & animation Level Select with working buttons & animation Background added directional lights added
v0.28 | iPhone builds begin
v0.29 | Added movement with arrows Added button input
v0.30 | Added ability to choose arrows or accelerometer for movement in options menu (rough version) Added movement for accelerometer Added ability to swip left/right to pan camera Added ability to zoom in/out with two-touch gesture Added code to register double-tap (not used yet)
v0.31 | Made button placement relative percentage of screen size Moved A & B buttons when arrows are not used Added 1-way jump pad to allow character to go up through bottom (rough version) Added 2-way jump pad to allow bouncing on both sides (rough version)